## Slide 1: Work Plan for the Ad Hoc Committee
The Education Coalition Leadership Group
June 15, 2021
Via Zoom

## Slide 2: Workload: August 2020 through April 2021
Ad Hoc Committee Activity | Number | Hours
Logistical Meetings with Co-Chairs | 12 | 5.25
Committee Meetings | 13 | 23.5
Total | 24 | 28.75
Does not include time organizing meetings, outreach to guest speakers, writing/editing papers, internal SES meetings, research on topic |  | 
Other Factor: 2020-21 meetings were in zoom format. Will meetings be in person going forward? |  | 

## Slide 3: Topics to Cover
Disproportionate Discipline of Black and Latinx Students
School Curriculum and Course Access
Hiring, Training, Placement and Retention of School Personnel
Facilities and Physical Plant
Other?

## Slide 4: Assumptions going forward
Do not want to lose momentum with current work
To the extent possible maintain current membership of Ad Hoc Committee
  Maintain current workload of 2 committee meetings/month
  Familiar with issue
  Familiar with consensus procedures of Ed Coalition
  Familiar with each other
  First paper was new experience; subsequent work should not take as long

## Slide 5: Suggested Workplan
Set goal of six months to complete each topic/paper:
  4 months for Research/meetings/convenings/etc.
  2 months to write/edit paper
  Four papers equals 24 months of work
Discussion point: It is suggested that we set goal to complete work in 12 months by increasing meetings to once/week during summer/Fall.

## Slide 6: Suggested Budget
Current SES Contract: $40,000 per year or $3,333.33 per month
Recommend Ad Hoc Committee contract of $3,000 per month
  Annual assessment per member: $4,500 [assumes PTA does not pay]
  No max on hours. Will take as many hours as is required to complete work
Other Expenses
  None for SES
  If move to in person format:
    Travel for guest speakers [if meeting format is ‘in person’?]
    Lunch for Ad Hoc Committee members?
  Other Costs?

## Slide 7: SES or Consultant
SES is interested in continuing the work, if compensated
  Worked with the Ed Coalition since 2012
  Familiar with procedures of Ed Coalition
  Has worked on Ad Hoc Committee issue the past year
  No learning curve
Consultant Considerations
  Time required to recruit, deliberate, interview and hire
  Even if outside consultant is hired, it is likely SES will have to engage in the administrative work of the Ad Hoc Committee
  Learning curve for new consultant to understand procedures of Ed Coalition

## Slide 8: Questions/Discussion